## Plan
ID | Workstream | Epic / Feature | Task / Activity / Milestone | Task Level | Domain | Progress % | Start Date | End Date
TG-01 | Test Governance | Test Strategy | Define programme test strategy | 1 | Governance | 100 | 01/04/2026 | 15/04/2026
TG-02 | Test Governance | Test Strategy | Agree entry/exit criteria across workstreams | 2 | Governance | 100 | 08/04/2026 | 22/04/2026
TG-03 | Test Governance | Test Strategy | Establish defect management process | 2 | Governance | 100 | 08/04/2026 | 22/04/2026
TG-04 | Test Governance | Test Reporting | Weekly test status report – wk1 | 2 | Governance | 100 | 15/04/2026 | 16/04/2026
TG-05 | Test Governance | Test Reporting | Weekly test status report – wk2 | 2 | Governance | 100 | 22/04/2026 | 23/04/2026
TG-06 | Test Governance | Test Reporting | Weekly test status report – wk3 | 2 | Governance | 80 | 29/04/2026 | 30/04/2026
TG-07 | Test Governance | Test Reporting | Programme test dashboard – Apr | 1 | Governance | 70 | 01/05/2026 | 02/05/2026
TG-08 | Test Governance | Test Reporting | Programme test dashboard – May | 1 | Governance | 0 | 01/06/2026 | 02/06/2026
SW-T01 | SWIFT Payments | Unit Testing | Unit test – MT103 outbound | 2 | Testing | 100 | 22/04/2026 | 29/04/2026
SW-T02 | SWIFT Payments | Unit Testing | Unit test – MT202 COV | 2 | Testing | 100 | 22/04/2026 | 29/04/2026
SW-T03 | SWIFT Payments | Unit Testing | Unit test – MX pacs.008 | 2 | Testing | 90 | 29/04/2026 | 06/05/2026
SW-T04 | SWIFT Payments | SIT | SIT cycle 1 – SWIFT outbound | 1 | Testing | 60 | 06/05/2026 | 20/05/2026
SW-T05 | SWIFT Payments | SIT | SIT cycle 1 – SWIFT inbound | 2 | Testing | 55 | 06/05/2026 | 20/05/2026
SW-T06 | SWIFT Payments | SIT | SIT cycle 2 – end-to-end SWIFT | 2 | Testing | 20 | 20/05/2026 | 03/06/2026
SW-T07 | SWIFT Payments | SIT | SIT defect fix & retest | 2 | Testing | 10 | 27/05/2026 | 10/06/2026
SW-T08 | SWIFT Payments | UAT | UAT scenario pack – SWIFT | 2 | Testing | 0 | 10/06/2026 | 24/06/2026
SW-T09 | SWIFT Payments | UAT | UAT execution – business users | 2 | Testing | 0 | 24/06/2026 | 08/07/2026
SW-T10 | SWIFT Payments | UAT | UAT sign-off | 1 | Testing | 0 | 08/07/2026 | 10/07/2026
SE-T01 | SEPA Payments | Unit Testing | Unit test – SCT initiation | 2 | Testing | 100 | 29/04/2026 | 06/05/2026
SE-T02 | SEPA Payments | Unit Testing | Unit test – SDD direct debit | 2 | Testing | 95 | 29/04/2026 | 06/05/2026
SE-T03 | SEPA Payments | SIT | SIT cycle 1 – SEPA Credit Transfer | 1 | Testing | 50 | 13/05/2026 | 27/05/2026
SE-T04 | SEPA Payments | SIT | SIT cycle 1 – SEPA Direct Debit | 2 | Testing | 45 | 13/05/2026 | 27/05/2026
SE-T05 | SEPA Payments | SIT | SIT cycle 2 – rejection & return flows | 2 | Testing | 15 | 27/05/2026 | 10/06/2026
SE-T06 | SEPA Payments | UAT | UAT scenario pack – SEPA | 2 | Testing | 0 | 17/06/2026 | 01/07/2026
SE-T07 | SEPA Payments | UAT | UAT execution & sign-off – SEPA | 1 | Testing | 0 | 01/07/2026 | 15/07/2026
CA-T01 | Card Payments | Unit Testing | Unit test – card authorisation | 2 | Testing | 100 | 22/04/2026 | 29/04/2026
CA-T02 | Card Payments | Unit Testing | Unit test – 3DS2 flow | 2 | Testing | 80 | 29/04/2026 | 13/05/2026
CA-T03 | Card Payments | SIT | SIT – card issuing end-to-end | 1 | Testing | 40 | 20/05/2026 | 03/06/2026
CA-T04 | Card Payments | SIT | SIT – acquiring gateway | 2 | Testing | 35 | 20/05/2026 | 03/06/2026
CA-T05 | Card Payments | SIT | SIT – tokenisation | 2 | Testing | 20 | 27/05/2026 | 10/06/2026
CA-T06 | Card Payments | Performance | Load test – card auth (500 TPS) | 2 | Performance | 10 | 03/06/2026 | 17/06/2026
CA-T07 | Card Payments | UAT | UAT – card issuing & acquiring | 1 | Testing | 0 | 24/06/2026 | 15/07/2026
AM-T01 | AML & Compliance | Unit Testing | Unit test – name screening | 2 | Testing | 100 | 15/04/2026 | 22/04/2026
AM-T02 | AML & Compliance | Unit Testing | Unit test – transaction monitoring rules | 2 | Testing | 85 | 22/04/2026 | 06/05/2026
AM-T03 | AML & Compliance | SIT | SIT – AML screening pipeline | 1 | Testing | 50 | 13/05/2026 | 27/05/2026
AM-T04 | AML & Compliance | SIT | SIT – sanctions watchlist refresh | 2 | Testing | 55 | 13/05/2026 | 27/05/2026
AM-T05 | AML & Compliance | Regression | Regression suite – AML rules | 2 | Testing | 25 | 27/05/2026 | 10/06/2026
AM-T06 | AML & Compliance | UAT | UAT – compliance officer scenarios | 1 | Testing | 0 | 17/06/2026 | 08/07/2026
IN-T01 | Infrastructure | NFT | Performance baseline – API gateway | 2 | Performance | 80 | 06/05/2026 | 20/05/2026
IN-T02 | Infrastructure | NFT | Soak test – 72 hr run | 2 | Performance | 30 | 27/05/2026 | 30/05/2026
IN-T03 | Infrastructure | Security | OWASP ZAP scan – non-prod | 2 | Security | 60 | 13/05/2026 | 20/05/2026
IN-T04 | Infrastructure | Security | Penetration test – external | 2 | Security | 20 | 27/05/2026 | 10/06/2026
IN-T05 | Infrastructure | DR | Disaster recovery test | 1 | Infrastructure | 0 | 17/06/2026 | 24/06/2026

## RAID
ID | Title | Description | Mitigation | Impact
R-001 | Test environment availability | Non-prod environments not stable; blocking SIT cycles | Engage TI workstream; daily stand-up on env health | High
R-002 | Test data – PII masking | Live-like data needed for UAT but PII masking not done | Data team to deliver masked dataset by 30-May | High
A-001 | UAT resource sign-off | Business UAT leads not confirmed for Card and SEPA | Programme Manager to confirm resource by 15-May | Medium
I-001 | SWIFT SIT cycle 1 slippage | SIT cycle 1 slipped by 5 days due to MT/MX schema issue | Schema fix deployed 22-Apr; retest scheduled | High
D-001 | Performance test tooling | LoadRunner licence not procured | Procurement raised; fallback to k6 open-source | Medium